## Sheet1
Bug report of Collectibles Network
Developer's name: | Mr.Avdhesh | Date:16th May 2018
Tester's name: | Niraj Kumar
S.n. | Screen/Module Page | Issue | Developer feedback | Test status | Completion Date | Comments
1 | Home | Spelling of " Entertenment" should be changed to "Entertainment"
2 |  | 404 error on clicking on first car
3 |  | PHP error on click on Cart icon
4 |  | All category should be dynamic
5 |  | "See all offers" not working
6 |  | Searching functionality is not working
7 |  | Toy: Add 70s separately and "2000 to present status" together
8 |  | Future page and retail& services pages are missing
9 |  | Instagram and tumbler pages are missing
10 |  | Add ons,blast ad pages are missing and follow functional doc
11 | Classified add | Post code number should not go in negative
12 |  | Insert confirmation message after adding ad
13 |  | Sometime PHP error after adding ad
14 | Login | Remove mousehover "Email" and insert "Username"
15 |  | Forgot password is not working
16 |  | In username and password keep placeholder same means capitalize both or keep camel case in both
17 | Menu | Help,safety tips,Community guidelines, links are not opening
18 |  | When terms& Conditions link is not opening then privacy policy page is opening
19 | My account | ad>> delete icon is not working
20 |  | message icon is not opening
21 |  | Editing is not functioning
22 |  | No ad is showing in featured ad
23 |  | When we selected other category then always setting category is selected
http://websiteandmobileappdevelopment.com/collectiblesnetwork/user/message
24 |  | Favourite>> 404 error occuring
25 | Latest listing | "See all offers" link is not opening
26 | Admin | New post ad: Error occuring