## Sheet1
| WEBSITE | IOS | ANDROID | BACKEND
UNIVERSAL STORE CHECKOUT
CHECKOUT NEEDS TO SPAN ALL PLATFORMS. | done |  | done Done
SO IF YOU START YOU CHECKOUT ON ONE PLATFORM AND
DECIDE TO FINISH LATER ON ANOTHER PLATFORM LATER, | done database work in tbl_cart
ITS THERE. | yes if login
TEST NOTE:
*TEST HOW PLATFORM IS WHEN BACKING OUT FROM PAYMENT OPTIONS
*TEST HOW PLATFORM IS WHEN BACKING OUT FROM PAYMENT OPTIONS
THEN REMOVE A ITEM FROM CART AND BACK OUT | done |  | done Done
CHECKOUT
NEED TO REMOVE THE PURCHASER INFO PAGE SINCE IT HAS TO BE | work on progress (need to disscus)
ENTERED WHEN PUTTING IN PAYMENT INFO
CUSTOMER EMAIL RECEIPT TRANSACTION
CUSTOMER NEEDS TO RECEIVE A EMAIL WITH PURCHASE DETAILS | done
FROM BOTH STORE AND FEATURE PURCHASES
AUTHORIZE.NET TRANSACTION EMAIL REPORT
AUTHORIZE.NET TRANSACTION EMAIL DOES NOT SHOW WHAT
WAS SOLD IN THE LINE ITEM SECTON FROM THE STORE OR FEATURE
PURCHASES | need to disscuss (will do later)
AD BUMP ON ALL FEATURES
FEATURED AD BUMPS ARE NOT BUMPING BACK INTO THE FIRST
POSITION EVERY SIX HOURS.
TEST NOTE.
PLACE A AD EVERY HOUR. IN THE TITLE STATE WHAT PALTFORM AND | need to disscuss (will do later)
TIME. PLACE FOUR ADS PER PLATFORM AT DIFFERENT TIMES, THEN
MONITOR ADS ACTIVITIES.
PICTURE ROATATING
THERE IS NO WAY TO ROTATE OF EDIT PICTURES TO THE RIGHT SIZE
LIKE ON THE APPS. PICTURES DON’T SHOW IN THE ORDER THEY ARE PICKED | need to disscuss provide screen shot
AD FEATURE PURCHASING
AD SHOULD NOT POST TILL AFTER TRANSACTION HAS TAKEN PLACE
TEST NOTE
TEST COMPLETEING FEATURE TRANSACTION, THEN TEST BACKING OUT
FROM PAYMENT OPTIONS. | need to disscuss
TEST CHANGING FEATURE OPTION (SELECT AD BUMP, CHECKOUT THEN
BACK OUT AND CHANGE TO SELECT ALL)
MESSAGING
CHANGE MESSAGING TO CHAT THREAD FORMATE ( LIKE A TEXT THREAD |  |  | done Done
ON YOUR CELL PHONE)
INFORMATION NEEDED TO BE BULIT INTO AD POST AND MESSAGE
DETAILS ON THE BACKEND | need to disscuss
NEED TO BUILD IN WHAT DEVICE WAS USE TO PLACE AD AND SEND
MESSAGE, SO THAT WAY IF WE NOTICED SOMETHING NOT WORKING
I DON’T HAVE TO ASK THE USER WHAT DEVICE THEY WERE USING. WE WILL
ALREADY KNOW
HOME PAGE NEEDS TO BE LIKE SUB CATERGORY PAGE.
Split the home page into two sections like the subcategory page. would like
the top of the home page to show the Home page advantage upgraded
features followed by the basic ad section. You can see how the
subcategory page was split into the Top of the Class section followed
by the basic ad section for reference. | need to disscuss
BANNERS ON BACKEND
NEED TO BE ABLE TO DRAG BANNERS UP AND DOWN INTO
DIFFERENT POSITION | done 15-oct database work
DELETE THE CONSTRAIN FUNCTION FROM POSTING PICTURES
PICTURES SHOULD ALWAYS BE WITHIN THE ORIGNAL WINDOW | need to disscuss
USER PAGE INFO
THE USER INFO NEEDS TO BE SEPRATED AT THE TOP OF THE PAGE
SHOULD SHOW IN BOTH CORNERS | need to disscuss
REPOST UPGRADED FEATURES
SELECT ALL IS NOT A OPTION ON REPOSTING ADS | need to discuss pleaseprovide screen
REPOST EMAIL CONFIRMATION
THE AD TITLE NEEDS TO BE ADDRESSED IN THE EMAIL | done 15-oct
REMOVE THE PHONE ICON
REMOVE THE PHONE ICON FROM THE CONTACT INFORMATION AND
FOOTER | done 14-10-2019
CHANGE PHONE ICON TO EMAIL ICON
CHANGE THE PHONE ICONE TO EMAIL ICON ON THE CONTACT US | Please provide screenshot
SECTION
POSTING A AD
SHOULD NOT BE ABLE TO POST UNLESS ALL FIELDS ARE FILLED OUT
BEFORE MOVING ON TO UPGRADED FEATURE PAGE. | done 15-oct |  | done Done
EMAIL SUBSCRIBER
THERE NEEDS TO BE A PLACE ON BOTH APPS TO ALLOW USER TO
SUBSCRIBE TO THE EMAIL |  |  | done Done
REMOVE SEE ALL OTHERS
REMOVE THE SEE ALL OTHERS OPTION AT THE BOTTOM OF THE HOME PAGE
UNDER THE ADS. | done
WEBSITE FOOTER
FOOTER LOOKS UNORGINIZED, SHORTCUTS NEED TO BE EVENLY DISPLACED | need to disscuss
SWIPE PAGE DOWN TO RELOAD PAGE
THE PAGE NEEDS TO RELOAD WHEN YOU PULL THE PAGE DOWN | need to discuss
SENDING A MESSAGE
YOU SHOULD NOT BE ABLE TO SEND A MESSAGE UNLESS THEIR HAS BEEN A | already fine
CHARACTER IN THE MESSAGE FIELD. THE WEBSITE IS SET UP THIS WAY.
MY ADS PAGE
CAN WE SET UP THIS PAGE, SO THAT AS YOU REPOST ADS THEY GO TO THE
BOTTOM OF THE LIST. THAT WAY YOU DON’T HAVE TO KEEP SCROLLING
THROUGH THE LIST TO FIND WHAT ADS NEED TO BE REPOSTED. REPOSTED
ADS WILL ALWAYS BE AT THE TOP OF THE LIST | done 11-0ct-2019
MY ADS PAGE
CAN YOU ADD A VEIW COUNT TO EACH AD POST. THE END USER WOULD
LIKE TO SEE IF THEY ARE GETTING ANY VIEWS | done
AD REMOVAL
CAN YOU SET IT UP SO THAT ADS THAT ARE INACTIVE FOR 6 MONTHS
AUTOMATICLY GET DELETED | Done