## Sheet1
Bug Report of Behale Android App
Date: 7th April2017
Developer's name |  | Sandeep Sir
Tester's name: |  | Niraj Kumar
S.N. | Screen/Module Page | Issue | Developer Feedback | Test Status | Compeletion Date | Comments
1 | Gender selection | Icon should be same size after selection | Done | Done | 7th April
2 |  | Place holder should be of same size | Done | Done | 7th April
3 |  | back , forward button and page indicator should be little up | Not issue
4 |  | Date of birth: Dropdown page should not be seems like double | Done
5 | Measurements | back , forward button and page indicator should be little up
6 | Work and sport | Icon should be flat | Done
7 |  | Toggle button should not be stretched | Done
Verification
8 |  | Questions toggle button should not be stretched | Done
9 |  | Do you agree:box should be more height
10 | Preferences | Settings: icons should be little large | Done
11 |  | Toggle button should not be thick | Done